Rename current dashboard to “Dashboard – Sales Manager”
DONE
Joe Done 18082022
Add new Dashboard called “Dashboard – Sales Manager”
Label to be “Sales Performance Dashboard”
All cards and charts will have the drill down functionality.
Drilling into them will open the reports related to the data

---
Use this page for cut off screens

---
Discounts given by employee.
Show % on chart bar.
Employee names down left.
% numbers across bottom.
Show the current leads list below these charts

---
Use current cards for all of the above boxes
When mouse hover over Cards show hint as per description below
Of where the card has got its values.
But cant drill down into
Cards
DONE Azhar Ali
24-08-2022
Joe Done 25082022
1) Task Is not drilling down
2) Rev chart colours starting at incorrect
amounts
Azhar Ali 270822
Fixed

---
Add “Dashboard Options” drop down
This will then display as “Dashboard – My” on menu.
Options will be
“All”, “Accounts”, “Executive”, “Marketing”, “Sales”,
“Sales Manager”
Add “Sales Quota”
Make name smaller
Azhar Ali
Already Done
Joe Done 25082022 BUT
It is still showing on the Dashboard Sales Manager
Even though I have set it to show on “Accounts” dashboard from
“Dashboard Options” on Employee Card
Azhar Ali 270822
Unable to understand

---
New Leads last 30 days
is new Lead/Customer source count for last 30 days.
Joe Display Done 18082022
New Quotes last 30 days
is new Quotes count for this month.
Not Pulling through
Accurate data
Azhar Ali 220822
Updated
Joe Done 25082022
Closed deals last 30 days
is new Invoice Value for last 30 days.
Closed deals Value last 12 months
is new Invoices value for last 12 months.

---
Win Rate
is last 30 days converted quotes to invoice count to
non-Converted quotes.
Average Sales Cycle
Is last 30 days average between quote date and converted to
invoice date.
Joe Display Done
Not pulling Accurate data
Azhar Ali 220822
Updated
Joe Done 25082022
Each Employee dial per last 30 days
Red is 40% of quota
Orange is 80% of quota
Green is 120% of Quota
Value at base is the employee invoice value sold
Dial is last 30 days of Invoices sold to quota

---
My Tasks
Is a list of Tasks from the CRM module.
Drilling into a task opens the actual task.
Drilling into the chart opens the CRM module.
My Calendar
Is a smaller version of the Appointment module
Drilling into an Appointment opens the actual appointment
Drilling into the chart opens the Appointment module
Why when clicking on
Calendar does it open
Customer list first?
Azhar Ali
Existing behavior
Joe Done 25082022 BUT
1) VS1 standard is not 100% correct on calendar
2) 3 Little dots not showing all charts to show and hide
Azhar Ali 270822
1) as we discussed on Skype
2) Fixed