Rename current dashboard to “Dashboard - Accounts”
Azhar Ali Done 12-08-2022
Joe Done 18082022
Add new Dashboard called “Dashboard - Sales”
Label to be “My Performance Dashboard”
Joe Done 18082022
Joe Not Done 18082022
Azhar Ali Done 221022
Joe Not Done 26082022
Drill down not working on some
Charts
Azhar Ali Fixed 270822
All cards and charts will have the drill down functionality.
Drilling into them will open the reports related to the data

---
Add “Dashboard Options” drop down
This will then display as “Dashboard – My” on menu.
Options will be
“All”, “Accounts”, “Executive”, “Marketing”, “Sales”,
“Sales Manager”
Add “Sales Quota”
Make name smaller
Already Done
Joe Already Done 25082022

---
Joe Done 18082022
Use current cards for all of the above boxes
Joe Done 18082022
When mouse hover over Cards show hint as per description below
Of where the card has got its values.
Azhar Ali Done 13-08-2022
Joe Not Done 18082022
Not pulling actual data
Azhar updated 220822
Joe Done 25082022
New Leads
is Lead count for last 3 months where status is “Unqualified”
“My Metric” is Leads with my name
“Team Average” is all leads for the same period

---
Add “Status” Drop down to lead/Customer cards.
Add employee drop down. Called “Rep”
Move “Is a Supplier” label to right of drop down
Make name smaller
Joe Done 25082022 BUT
Default Status not correct data being pulled
Because it's currently not displaying Unqualified,
Opportunity, Quoted, Invoiced
Azhar Ali 270822
working fine on my end
Add Source drop down.
Default values are “Google”, “Phone”, “Search Engine”,
“Unknown” (Default)
User can add to this list at any time
Default values for Status are “Unqualified” (Default),
“Opportunity”' “Quoted”, “Invoiced”
Azhar Ali Done 220822
Joe Not Done 25082022
Lead is dissapearing from Lead List
when invoiced. Canot test the status update
Azhar Ali 270822
It’s the existing behavior
User can add to this list at any time
Status updates automatically to “Quoted” if a quote is created.
Status updates automatically to “Invoiced” if a Invoice is created.
Make Skype ID field smaller

---
Azhar Ali Done 13-08-2022
Joe Cant Test. Cant add Lead Status
No Data pulling through
Azhar Ali 220822
Fixed add lead status issue
Joe Done 25082022 BUT
Lead is getting removed from Lead List
Azhar Ali 270822
existing behavior
New Opportunities
is Lead count for last 3 months where status is “Opportunity”
“My Metric” is Leads with my name
“Team Average” is all leads for the same period
Quoted Opportunities
is Lead/Customer count for last 3 months where a quote
has been made.
“My Metric” is Lead/Customer with my name
“Team Average” is all Lead/Customer for the same period
Won Opportunities
is Lead/Customer count for last 3 months where an Invoice
has been made
“My Metric” is Lead/Customer with my name
“Team Average” is all Lead/Customer for the same period

---
Azhar Ali Done 13-08-2022
Joe Cant Test. Cant add Lead Status
No data pulling though
Azhar Ali 220822
Updated
Joe Done 25082022 BUT
Edit chart in My Performance Dashboard not
showing all charts from all dashboards when wanting
to hide or show charts
Azhar Ali 270822
Fixed
Win Rate %
is Quote count for last 3 months where it is converted to an invoice
“My Metric” is Lead/Customer with my name
“Team Average” is all Lead/Customer for the same period
Average Sales Cycle
is average time taken where Lead/Customer status is converted
from “Unqualified” to “Invoiced”
“My Metric” is Lead/Customer with my name
“Team Average” is all Lead/Customer for the same period
Pipeline Amount
is quotes from Lead/Customer for last 3 months where the
quote has not been converted to an invoice.
“My Metric” is Lead/Customer with my name
“Team Average” is all Lead/Customer for the same period

---
Gap to Quota
is value of Invoices for last 3 months
If more than “Quota” on employee card show “In Front” and
colour Numbers green.
If less than “Quota” on employee card show “Behind” and
colour Numbers Red.
Azhar Ali Done 13-08-2022
Joe Not Done 18082022
Only displaying hard coded
Data
Azhar Ali 220822
Done
Joe Done 25082022

---
Sales Performance vs Quota
Is chart of Quota amount for last 6 months
Is chart of Quotes per month for last 6 months
Is chart of Invoices per month for last 6 months
Open Opportunities vs Source
Is chart of Lead/Customer count for last 6 months where a quote
has been made.
Is chart of top 3 source counts for last 6 months where a quote
has been made.

---
My Tasks
Is a list of Tasks from the CRM module.
Drilling into a task opens the actual task.
Drilling into the chart opens the CRM module.
Joe Done 18082022
My Calendar
Is a smaller version of the Appointment module
Drilling into an Appointment opens the actual appointment
Drilling into the chart opens the Appointment module

---
Show the current leads list below these charts
Joe Done 18082022