Add Refresh button
Jin Done 28072022
Joe Done 28072022
Add Refresh button

---
Display to hide side menu iPhone display
Jin Done
Joe 21072022

---
Jin Done
Joe 21072022
iPhone Appointment view …..... Not Good !

---
Need the ability to “Back Date” an Appoinment
Using creation date ??
Jin Done 28072022
Joe Done 28072022

---
Add the ability to flag an Employee as Unavailable if on “Leave” or
“Sick Leave”. Add column with button to existing list, when pressed will
Open date range options same as on appointment.
Appointments can't be booked against this Employee
Ibrar Ali Done 29-08-2022

---
Can't create an appointment for some employees from the
Allocations screen but can from the Appoinments screen
example David Jones
simon1clive@gmail.com
Simon@123
Jin Done 28072022
Joe Done 28072022

---
Ibrar Ali Done 29-08-2022
th
10 Appointments on 13
 July
After using Repeat Appointment all other appointments have been
Wiped from the Appointment and Allocation screens, but still
display in the list
See next page

---
Should be displaying 10 Different Appointments for this day
simon1clive@gmail.com
Simon@123
Ibrar Ali Done 29-08-2022

---
Selected Save on a new Appointment
Appointments already created for this Employee without issue.
Jin Done 04082022
Joe Done 04082022

---
Add a column to display the Appointment Product/Service
Jin Done 04082022
Joe Not Done 04082022
Turned off Product/Service column but
still displays but header disappears

---
Their is currently no Access level in VS1
For this. You cannot edit times on the
Appointment. You can only edit Actual
Start time if appointment hasn't stopped.
That's All. You cannot edit Breaks or end
Times or anything once an appointment is
Stopped.
Add the ability for a full access user to edit Appointment Times.
Need to edit start / stop times and add breaks as required
Add the ability for a full access user to edit Timesheet Times.
Need to edit start / stop times and add breaks as required
Jin Done – Breaks are introduced in
the application
Joe (There has always been breaks in
application. What am I supposed to test?)

---
Load Completed Appoinments to Timesheets automatically.
This was working??
These timesheets will then be used in payroll
Ibrar Ali Done 29-08-2022

---
Add Appointment Attachments to the Invoice when converted
Ibrar Ali Done 29-08-2022

---
Change label to “Product/Service for Appointment”
Working on it but
required more clarification
Add button for “Extra Product/Service Fees”
When selected, pop up form opens to allow additional products
to be charged to the appointment.
Use same functionality as on a invoice, ie auto open product list
Like when selecting a product in an invoice.
Change colour of button if products selected. Re-opening allows
To edit and add. Same as invoice
When converting appointment to invoice, these products will also load.

---
On Stop Appointment, expand the “Stop Appointment” popup to show
the summary of products/services sold.
They can add or remove products/services again, same as entering a
Product/service form, but also show the Notes field with the following
Message:
Enter Extra Work Done and Materials Used.
Working on it but
required more clarification